IMPACT II Evaluation Plan

(Example – Items in bold are part of the template)

| Why did you do it? (Objective): Teachers integrate technology into lessons |  |  |
| --- | --- | --- |
| What did you do? (Strategy): Provide professional development Activities: - Provide small group professional development on project-based learning during grade-level planning meetings. - Technology Facilitator and Media Coordinator provides one-on-one on training on utilizing United Streaming. - Provide large group “Introduction to Laptops” training |  |  |
| Evaluation Questions | Measures/Data Sources | Results |
| What do you need to know? | How will you find out? | What were the results? |
| Which teachers participated in the professional development? (strategy) | Rosters for each training session | - All 6th, 7th, and 8th grade teachers participated in PBL training during grade-level planning meetings - 20 teachers participated in United Streaming training - 50 teachers participated in laptop training |
| Did teachers think the professional development was beneficial? (strategy) | Professional Development Questionnaires (PDQs) for each session | - 95% of respondents SA or A that the PD during grade-level planning meetings was beneficial - 90% of respondents SA or A that the United Streaming training was beneficial - 75% of respondents SA or A that laptop training was beneficial |
| ARE teachers using what they learned in professional development in the classroom to integrate technology into lessons? (objective) | Review of lesson plans LoFTI | - 50% of teachers who participated in PBL training planned a lesson that included PBL - 25% of teachers who participated in United Streaming planned a lesson that included a video from United Streaming - 100% of teachers who participated in laptop training were observed using laptops |
| Decisions (Guiding Questions: What do the results mean? What are you going to do now?) - Summary of Results (Interpretation of Data): What do the results mean? - Participation in PD seemed to be dependent upon the delivery method and content. Providing training through various deliveries seemed to suit the needs of the teachers. A good way to ensure all teachers received PD is for the TF and MC to go to the grade level planning meeting. - Teachers seemed to respond positively to all the professional development sessions offered. They seemed to find the training provided during the grade level planning meetings most beneficial and the fewest percentage of staff found the large-group training beneficial. - Teachers used the laptops provided on a regular basis despite results of the PDQ. An unsatisfactory amount of teachers used PBL and United Streaming in their lessons. Additional data is needed to determine why more teachers did not use the PBL and United Streaming in their lessons. - Next Steps (Action Steps): What are you going to do now? - TF and MC will continue to attend grade level planning meetings and will provide professional development during those meetings as requested by the grade-level teams. TF & MC will also use this time to determine what, if any additional professional development sessions need to be offered to the whole staff or as optional, small group sessions. - Conduct a focus group of a sample of teachers to collect data to determine why many teachers did not use the United Streaming and PBL in their lessons. Determine what State of Concern issues might need to be addressed for those not implementing United Streaming and PBL in their lessons. - Use STNA to identify professional development needs for next year, and then check the list of possible topics with teachers during grade level meetings. |  |  |